## Group5_Estimated_Effort
Task Name: (Dependencies top to bottom) | [6 empty] | Color means not finished and moved to next iteration |  | Ben | Donald | Neil | Total
|  |  | Role | Owner | Estimated | Effort | Actual | Actual | Actual | Actual | Actual
|  |  |  | (primary owner) (secondary owners) | By Task | Subtotals | By Task | Subtotals | By Task | By Task | By Task
Preliminary &
Parallel Tasks | Architecture |  |  |  |  | 10 |  | 8 | 2 | 4 | 2 | 8
|  | Design architecture | Project Manager | Ben, Donald, Neil | 10 |  | 8 |  | 2 | 4 | 2
| Requirements |  |  |  |  | 9 |  | 9 | 2.5 | 2.5 | 4 | 9
|  | Gather | Requirements Engineer | Ben, Donald, Neil | 2 |  | 2 |  | 0.5 | 0.5 | 1
|  | Analyze | Requirements Engineer | Ben, Donald, Neil | 4 |  | 4 |  | 1 | 1 | 2
|  | Specify | Requirements Engineer | Ben, Donald, Neil | 3 |  | 3 |  | 1 | 1 | 1
| Documentation |  |  |  |  | 28 |  | 19 | 11 | 5 | 3 | 19
|  | Project Charter | Project Manager | Ben, Donald, Neil | 2 |  | 4 |  | 3 | 1
|  | Release Plan | Project Manager | Ben, Donald, Neil | 2 |  | 0
|  | Requirements Document | Project Manager, Requirements Engineer | Ben, Donald, Neil | 5 |  | 8 |  | 6 | 1 | 1
|  | Project Plan | Project Manager, Developers | Ben, Donald, Neil | 5 |  | 7 |  | 2 | 3 | 2
|  | Architecture Document | Architect | Ben, Donald, Neil | 4 |  | 0
|  | Test Report | Tester | Ben, Donald, Neil | 8 |  | 0
|  | User Guide & System Admin Doc | Developers, Requirements Engineer | Ben, Donald, Neil | 2 |  | 0
Iteration 1: | Design |  |  |  |  | 43 |  | 28 | 7 | 11 | 10 | 28
|  | Determine technology needs | Developer | Ben, Donald, Neil | 1 |  | 1 |  | 0 | 1
|  | Create Database Schema | Architect | Donald, Neil | 5 |  | 1 |  |  |  | 1
|  | Test Plan | Tester | Ben, Neil | 2 |  | 2 |  | 1 |  | 1
|  | Research C# Language | Developer | Ben, Donald, Neil | 18 |  | 21 |  | 5 | 8 | 8
|  | Plan SQL Commands | Developer | Ben, Donald, Neil | 13 |  | 1 |  | 1
|  | Outline General Implementation Process and major goals | Architect | Ben, Donald, Neil | 4 |  | 2 |  |  | 2
| Development |  |  |  |  | 10 |  | 4 | 1 | 2 | 1 | 4
|  | Create C# Environment | Developer | Ben, Donald, Neil | 1 |  | 2 |  | 1 |  | 1
|  | Create SQL DB | Developer | Ben, Donald, Neil | 4 |  | 1 |  |  | 1
|  | Begin Building SQL Database | Developer | Ben, Donald, Neil | 5 |  | 1 |  | 0 | 1
| Analysis |  |  |  |  | 4 |  | 5 | 2 | 2 | 1 | 5
|  | System Testing | Tester | Ben, Donald, Neil | 2 |  | 0 |  | 0 | 0
|  | Evaluate needs for next iteration | Project Manager | Ben, Donald, Neil | 2 |  | 5 |  | 2 | 2 | 1
Iteration 2: | Design |  |  |  |  | 11 |  | 14 | 5 | 3 | 6 | 14
|  | Create Database Schema | Architect | Donald, Neil | 4 |  | 4 |  | 2 | 1 | 1
|  | Plan SQL Commands | Developer | Donald, Neil | 4 |  | 3 |  | 1 | 1 | 1
|  | Design Prototype | Architect, Developer | Ben, Donald, Neil | 3 |  | 7 |  | 2 | 1 | 4
| Development |  |  |  |  | 35 |  | 42 | 11 | 13 | 18 | 42
|  | Create SQL DB | Developer | Donald, Ben | 3 |  | 2 |  | 1 | 1
|  | Build SQL DB | Developer | Donald, Ben | 4 |  | 4 |  | 1 | 1 | 2
|  | Implement Set Budget Feature | Developer | Ben, Neil | 6 |  | 12 |  | 4 | 4 | 4
|  | Implement Budget Tracking | Developer | Neil, Ben | 8 |  | 4 |  | 0 | 2 | 2
|  | Implement Budget Adjustment | Developer | Ben, Neil | 6 |  | 4 |  | 0 | 2 | 2
|  | Implement size responsive Prototype UI | Developer, UX/UI | Neil, Donald | 4 |  | 8 |  | 3 | 1 | 4
|  | Integrate Prototype components | Developer | Ben, Donald, Neil | 4 |  | 8 |  | 2 | 2 | 4
| Analysis |  |  |  |  | 8 |  | 10 | 2.5 | 2.5 | 5 | 10
|  | System Testing | Tester | Neil, Donald | 2 |  | 2 |  | 0.5 | 0.5 | 2
|  | Prototype Testing | Tester | Ben, Neil | 2 |  | 4 |  | 1 | 1 | 2
|  | Evaluate needs for next iteration | Project Manager | Ben, Donald, Neil | 4 |  | 4 |  | 1 | 1 | 1
Iteration 3: | Design |  |  |  |  | 21 |  | 21 | 11.5 | 6 | 3.5 | 21
|  | Review Prototype and identify shortcomings and adjustments | Project Manager, Architect, Developer | Ben, Donald, Neil | 4 |  | 4 |  | 0.5 | 3 | 0.5
|  | Plan UI/UX Component needs and quality enhancing features | UX/UI | Neil, Donald | 2 |  | 2 |  |  | 2
|  | Design Goals-Budget-Rewards/Achievement Interactions | Developer | Ben, Donald, Neil | 5 |  | 5 |  | 3 |  | 2
|  | Complete Architecture Document | Project Manager, Architect | Ben, Neil | 4 |  | 6 |  | 6
|  | Design User Guide and complete sections established by prototype | Project Manager, Developer, Architect | Ben, Donald | 6 |  | 4 |  | 2 | 1 | 1
| Development |  |  |  |  | 27 |  | 9 | 3 | 4 | 2 | 9
|  | Rebuild streamlined version of prototype | Developer | Ben, Donald, Neil | 5 |  | 2 |  |  | 2
|  | Implement Goals Component | Developer | Ben, Neil | 3 |  | 3 |  | 3
|  | Implement Rewards Component | Developer | Donald, Ben | 3 |  | 0
|  | Integrate Goal, Budget, and Reward/Achievement Components | Developer | Ben, Donald, Neil | 6 |  | 0
|  | Complete Sample DB Migrations | Developer | Neil, Donald | 2 |  | 2 |  |  | 2
|  | Complete UI Partial Views for completed components | UX/UI, Developer | Neil, Donald | 5 |  | 2 |  |  |  | 2
|  | Add Goals and Rewards entities to SQL Database | Developer | Donald, Ben | 3 |  | 0
| Analysis |  |  |  |  | 11 |  | 13 | 3 | 5 | 5 | 13
|  | System Testing and Review | Tester | Ben, Donald, Neil | 5 |  | 5 |  | 1 | 2 | 2
|  | Database Testing and Review | Tester | Ben, Donald | 3 |  | 5 |  | 1 | 2 | 2
|  | Evaluate needs for next iteration | Project Manager | Ben, Donald, Neil | 3 |  | 3 |  | 1 | 1 | 1
Iteration 4: | Design |  |  |  |  | 5 |  | 6 | 0 | 4 | 2 | 6
|  | Final UI Design |  | Donald | 5 |  | 6 |  | 0 | 4 | 2
| Development |  |  |  |  | 27 |  | 26 | 12 | 8 | 6 | 26
|  | Implement Single Page Features to UI |  | Donald, Ben | 5 |  | 1 |  | 0 | 1 | 0
|  | Rebuild streamlined version of prototype |  | Donald, Ben | 3 |  | 7 |  | 7
|  | Refactor Database and Migrations |  | Neil, Donald, Ben | 4 |  | 4 |  |  | 4
|  | Implement Rewards Component |  | Ben, Neil | 3 |  | 4 |  | 2 | 2
|  | Integrate Goal, Budget, and Reward/Achievement Components |  | Ben, Neil | 6 |  | 4 |  | 3 | 1
|  | Complete UI Partial Views for completed components |  | Neil, Donald | 3 |  | 2 |  |  |  | 2
|  | Add Goals and Rewards entities to SQL Database |  | Ben, Donald | 3 |  | 4 |  |  |  | 4
| Analysis |  |  |  |  | 11 |  | 10 | 2 | 3 | 5 | 10
|  | System Testing and Review | Tester | Ben, Neil | 2 |  | 2 |  |  |  | 2
|  | Database Testing and Review | Tester | Neil, Donald | 3 |  | 3 |  |  | 1 | 2
|  | Evaluate needs for next iteration | Project Manager | Ben, Donald, Neil | 6 |  | 5 |  | 2 | 2 | 1
Iteration 5: | Design |  |  |  |  | 2 |  | 0
|  | Review and Implement Final UI Changes |  | Donald, Ben, Neil | 2
| Development |  |  |  |  | 41 |  | 0
|  | Implement Single Page Features to UI |  | Donald, Ben | 4
|  | Integrate Goal, Budget, and Reward/Achievement Components |  | Ben, Neil | 2
|  | Integrate Components for Users |  | Neil, Ben, Donald | 5
|  | Create Admin Functionality |  | Neil, Ben, Donald | 5
|  | Clean Code |  | Donald, Neil | 5
|  | Finalize Code and Finish Project |  | Ben, Neil, Donald | 10
|  | Develop/Run Tests |  | Ben, Neil, Donald | 10
| Analysis |  |  |  |  | 4
|  | System Testing and Review | Tester | Ben, Neil | 2
|  | Database Testing and Review | Tester | Neil, Donald | 2
[5 empty] | 307 |  | 224 | 224 | 75.5 | 75 | 73.5 | 224
Total